Empathease

Project Status Review

AMD Slingshot Competition  ·  Deadline: March 1, 2026  ·  8 Days Remaining

Where We Stand The model stack is 100% complete and locked. All five criteria gates passed. Three of five remaining components are integration work — wiring things that exist. The therapy engine system prompt is written and ready to load. The largest open risk is frontend + end-to-end integration, not model quality. 8 days is enough if integration starts today.

1 · What's Complete

1.1  Model Stack — Fully Locked 🔒

| Component | Details | Status | Key Metric |
| --- | --- | --- | --- |
| Facial Emotion Recognition | EfficientNet-B0 · 50MB · PyTorch · CLAHE preprocessing | ✅ LOCKED | 73.75% on Indian faces val |
| Text Emotion Model v2.1 | MuRIL-base-cased · 8 classes · CrossEntropyLoss · 73k training examples | ✅ LOCKED ef86e4deb8a57c4b | 74.4% macro F1 |
| fear_disambiguator.py | 4 post-processing rules · no retraining needed | ✅ DONE — 6/6 unit tests | Fixed 5 multi-turn failures |
| Multi-turn correctness | 30 hand-crafted test cases · [TURN_1]…[CURRENT] format | ✅ GATE PASSED | 26/30 (86.7%) — gate ≥83.3% |
| Vocal Tone Analysis | Wav2Vec2 · HuggingFace pretrained · valence + arousal | ✅ Code complete | Needs integration testing |

1.2  Data Pipeline — Complete

| Asset | Size | Status |
| --- | --- | --- |
| GoEmotions remapped (28→8 class) | ~43,000 examples | ✅ Done |
| Bhaav dataset | ~16,000 examples (5 class, Hindi comprehension) | ✅ Done |
| Hinglish Therapy CSV v2 | 12,000 examples · 8 classes · STT noise + multi-turn | ✅ Done |
| Synthetic suppressed | ~2,000 examples | ✅ Done |
| Total | ~73,000 — stratified 80/10/10 split | ✅ Done |

1.3  Knowledge Base + System Prompt — Complete

| File | Purpose | Status |
| --- | --- | --- |
| system_prompt_v1.md | Production therapy engine system prompt — integrates TextAnalysisResult schema, all frameworks, India-first crisis resources, Hinglish vocab | ✅ Done |
| hinglish_therapeutic_language.md | Hinglish emotional vocabulary, distress phrase mapping, formality register rules | ✅ Done |
| indian_context.md | Collectivist family dynamics, stigma, gender, academic pressure, LGBTQ+, socioeconomic context | ✅ Done |
| crisis_protocol.md | Crisis levels + hard-coded urgent protocol | ✅ Done |
| cognitive_distortions.md + skills.md + grounding_techniques.md | CBT, DBT, somatic frameworks | ✅ Done |
| core_principles.md + meaning_making.md | Person-Centered (Rogers) + Logotherapy (Frankl) | ✅ Done |
| Understanding anxiety / depression / stress | Psychoeducation modules — post-March 1 RAG retrieval | ✅ Done (future RAG) |

1.4  Architecture + Planning Artifacts

| Artifact | Status |
| --- | --- |
| System architecture diagram (interactive HTML) | ✅ Done — all 7 layers, animated, STT fallback cascade visualized |
| TextEmotionModel v2.1 implementation plan (docx) | ✅ Done — executed in full |
| MODEL_LOCK.json | ✅ Done — hash ef86e4deb8a57c4b, all gates recorded |
| test_multi_turn.py — 30-case test suite | ✅ Done — gate passed at 26/30 |
| AirLLM decision | ✅ Decided — not using (2 tok/s too slow for therapy context) |

2 · What's Left — 8 Days

2.1  Complete Priority Map

| Priority | Component | Effort | Blocks |
| --- | --- | --- | --- |
| P0 — Must ship | Multimodal Fusion Layer | 2 days | Everything — therapy engine can't run without it |
| P0 — Must ship | Therapy Engine (LLM wiring) | 1 day | The demo — this is what users experience |
| P0 — Must ship | Crisis Hard-Code Protocol | 0.5 day | Non-negotiable before any public demo |
| P0 — Must ship | Frontend (WebSocket + FER overlay + chat) | 2–3 days | Demo vehicle — judges need to see it working |
| P1 — Should ship | Sarvam STT + TTS integration | 1 day | High visual impact — makes demo feel real |
| P2 — Nice to have | Rule-based layers (trajectory, cognitive, flags) | 1–2 days | Deepens therapy quality — demo works without |
| P2 — Nice to have | Session storage (PostgreSQL) | 0.5 day | Memory across sessions — not needed for live demo |
| Post-March 1 | RAG retrieval over KB files | — | Not needed before deadline |

3 · P0 Work — Detailed Breakdown

3.1  Fusion Layer  ·  Highest Risk Item

This is the only component with real architectural uncertainty. Everything else is wiring known pieces.

| Sub-task | What needs to happen | Risk |
| --- | --- | --- |
| Weight computation | STT confidence maps to weights: HIGH→Text 60/Vocal 30/FER 10, MEDIUM→35/45/20, LOW→0/60/40 | Low — logic is defined |
| Stream synchronization | FER runs at ~10fps, vocal runs in chunks, text runs per utterance — need to align timestamps | Medium — timing logic |
| Incongruence detection | Flag when face emotion and text emotion diverge by >2 class positions in valence space | Low — rule-based |
| Fallback when all uncertain | Context history prior — use last 3 fused states to inform current if all streams low confidence | Low — carry-forward logic |
| Output schema | Produce full FusedEmotionalState feeding system_prompt_v1.md's EMOTIONAL_STATE block | Low — schema is defined |

⚠️ Critical: Fusion Layer is the System's Spine Every other component either feeds into fusion (FER, text, vocal) or reads from it (therapy engine, crisis protocol). Build and test fusion in isolation BEFORE wiring the therapy engine. Test with mocked model outputs first — don't wait for all three models to be running simultaneously. A 30-minute mock integration test (hardcoded FusedEmotionalState → therapy engine) will catch system prompt issues early.

3.2  Therapy Engine  ·  1 Day

System prompt is written (system_prompt_v1.md). The wiring work is:

- Load system_prompt_v1.md as system message on session start

- Inject EMOTIONAL_STATE block before each user message (from fusion output)

- Set up Ollama / Groq / Claude API switcher based on environment variable

- Stream tokens back via WebSocket — don't wait for full response

- Maintain conversation history in memory per session (no DB needed for demo)

- Hard-code: if crisis_level = urgent → bypass LLM entirely → serve crisis template

Ollama → Groq → Claude API Ladder Dev: OLLAMA_HOST=localhost → Llama 3.1 8B → free, ~12 tok/s on GTX 1650 Demo prep: GROQ_API_KEY=... → Llama 3.1 70B → free tier, ~280 tok/s Production: ANTHROPIC_API_KEY=... → Claude API → paid, best quality Switch via single env var: LLM_BACKEND=ollama¦groq¦claude For the AMD Slingshot demo: use Groq (70B quality, zero latency, free).

3.3  Crisis Hard-Code  ·  0.5 Day

This must be deterministic — never LLM-dependent. Implement as middleware that intercepts before the LLM call:

if crisis_level == 'urgent':

return CRISIS_TEMPLATE_HINGLISH  # hard-coded, no LLM call

flag_for_human_review(session_id)

# NEVER reaches LLM

Crisis template is already written in crisis_protocol.md and system_prompt_v1.md. Just needs to be extracted into a constant and wired as middleware.

3.4  Frontend  ·  2–3 Days  ·  Demo Vehicle

This is the highest time risk. The frontend is what judges interact with. It needs to work reliably, not perfectly.

| Feature | Priority | Notes |
| --- | --- | --- |
| WebSocket audio capture + streaming | Must have | MediaRecorder API → Sarvam STT → text model pipeline |
| Text chat input fallback | Must have | If audio fails during demo, text input must work. Never demo without this fallback. |
| Therapy response display (streaming) | Must have | Stream tokens to screen as they arrive — don't wait for full response |
| FER emotion overlay on webcam | Should have | Real-time face emotion displayed on video. High visual impact for judges. |
| Emotion state indicator | Should have | Small UI element showing current detected emotion + confidence. Shows the multimodal pipeline working. |
| Sarvam TTS audio playback | Should have | Response plays as audio. Makes it feel like a real therapy companion. |
| Session history / transcript | Nice to have | Useful but not demo-blocking |
| Mobile responsive layout | Nice to have | Post-deadline polish |

Demo Reliability Rule: Build the Fallback First Before building FER overlay and Sarvam TTS — make sure text input → LLM → text response works perfectly. If audio breaks during the live demo, you need text input to work seamlessly. A demo that gracefully degrades beats one that crashes spectacularly.

4 · P1 Work — Sarvam Integration

Both Sarvam components are well-defined. Integration is the work, not design.

| Component | Integration task | Time estimate |
| --- | --- | --- |
| Saaras STT | WebSocket connection to Sarvam API · feed audio chunks · receive transcript + confidence scores · route confidence to fusion weight cascade | 4–6 hours |
| Bulbul TTS | Send therapy engine text response to Sarvam TTS endpoint · stream audio back to frontend · pace control 0.9× for therapeutic feel | 2–3 hours |
| Language detection routing | STT returns detected language → route to correct TTS voice (en-IN vs hi-IN) · inform text model for Hinglish handling | 1–2 hours |

5 · P2 Work — Rule-Based Layers (Post-Demo OK)

These deepen therapy quality significantly but the demo works without them. The system prompt already handles trajectory and flags in its response logic — these services formalize it.

| Service | File | What it does | Build time |
| --- | --- | --- | --- |
| Trajectory Tracker | emotion_trajectory.py | Sliding window over last N emotions → escalating/stabilizing/flat/volatile/improving + session arc after turn 5 | 3–4 hours |
| Cognitive Pattern Detector | cognitive_patterns.py | Keyword + syntax matching for 6 CBT distortion types · EN + HI + Hinglish pattern sets | 3–4 hours |
| Therapeutic Flags | therapeutic_flags.py | Composite logic: first_disclosure, breakthrough_moment, repetition_pattern, needs_grounding, ready_to_go_deeper | 2–3 hours |
| Register Detector | language_detection.py (extend) | Add formality register: formal/informal/distressed_slang · code-switch frequency | 1–2 hours |

6 · Suggested Day Plan — 8 Days Remaining

| Day | Focus | End-of-day target |
| --- | --- | --- |
| Day 5 | Fusion Layer | FusedEmotionalState produced from mocked model outputs. All 4 STT fallback weight cases verified. Incongruence detection working. |
| Day 6 | Therapy Engine wiring | Ollama running with system_prompt_v1.md. EMOTIONAL_STATE injected per turn. Crisis bypass hard-coded. End-to-end: text input → LLM → text response. |
| Day 7 | Frontend core | WebSocket audio capture working. Text input fallback working. Streaming response display working. Basic FER overlay on webcam. |
| Day 8 | Sarvam integration | Saaras STT producing transcripts with confidence scores. Bulbul TTS playing responses back. Fusion weights switching based on STT confidence. |
| Day 9 | Full integration test | 10-turn simulated therapy session working end-to-end. All three models live. Crisis protocol tested. Demo script rehearsed once. |
| Day 10 | Buffer + polish | Fix integration bugs found on Day 9. Emotion state UI indicator. Demo script rehearsed three times. Fallback scenarios tested. |
| Day 11 | Demo day prep | Final rehearsal. All fallbacks verified. Backup: pre-recorded session video if live demo fails. |
| Day 12 (Mar 1) | Submission | Submit. Rest. |

Most Important Risk to Manage The frontend is the highest time risk — 2–3 days is optimistic if WebSocket audio capture is complex. Day 7 end target is the critical milestone to watch. If you're not there by end of Day 7, cut Sarvam TTS from the live demo and replace with text-only responses. A working text demo with FER overlay is far stronger than a broken audio demo.

7 · Files Delivered This Sprint

| File | Purpose | Reuse in build |
| --- | --- | --- |
| hinglish_therapy_emotion_dataset_v2.csv | 12,000-example training dataset · 8 classes · multi-turn · STT noise | Training complete — archived |
| MODEL_LOCK.json | Model version record · hash · training config · all gate results | Reference during integration |
| test_multi_turn.py | 30-case correctness test suite · runner · CSV export · distribution analysis | Re-run after any model changes |
| fear_disambiguator.py | Post-processing patch · 4 rules · 6 unit tests | Load in text_emotion.py — see integration snippet in file |
| TextEmotionModel_v2_ImplementationPlan.docx | Full implementation plan with all corrections from v1 | Reference only |
| empathease_architecture.html | Interactive system architecture diagram · all 7 layers | Share with judges / stakeholders |
| system_prompt_v1.md | Production therapy engine system prompt · schema-aware · India-first | Load as system message on session start |
| cognitive_patterns_patch.py | Cognitive pattern detection rules · CBT distortion patterns in EN+HI+Hinglish | Load in cognitive_patterns.py service |

Empathease  ·  Project Status Review  ·  Feb 23, 2026  ·  8 days to AMD Slingshot deadline